## 2018-2020
GOAL: Humanitarian responders and development actors have the knowledge, skills and tools to implement quality and coordinated child labour in emergencies preparedness, prevention and response actions.
2018-2020 | [12 empty] | 2018
OBJECTIVE | ACTIVITIES / Sub-Activities | INDICATORS | 1-Year TARGET 2018 | 3-Year Target 2018-2020 | LEAD | CONTRIBUTING PARTNERS | Linkages with other WGs and TFs | 2018 | 2019-2020 | ACHIEVEMENTS | BUDGET REQUIRED 2018 | BUDGET DESCRIPTION | BUDGET FUNDED | FUNDING SOURCE
1. Technical tools, standards and guidance: Inter-agency technical guidance, standards and tools to prevent and respond to (the worst forms of) child labour in emergencies are available and reflect the latest evidence and lessons learned. | 1.1 CL Toolkit: Finalise Toolkit based on new evidence and feedback and knowledge gathered during field-testing phase. | Number of global CL toolkits developed and published as inter-active PDF. |  | 1 Child Labour in Emergencies Toolkit. | Plan International, Alyson Eynon, independent consultant | CLTF members to sign up here |  | 2018-09-01 |  |  | 30000 | 20000 - Consultancy fees; 10000 - interactive PDF design | 30000 | Plan International | 30
| 1.1.1 CL Toolkit: Collect and compile feedback on Child Labour in Emergencies toolkit | Number of consultations to collect feedback completed |  | 1 consultation (incl. 10 KI interviews, 3 online group discussions, minimum 50 surveys completed) | Plan International, Alyson Eynon, independent consultant |  |  | Jan-Feb 2018
| 1.1.2 CL Toolkit: Update Toolkit based on feedback and knowledge gathered during field-testing phase. | Number of global CL toolkits developed and published as inter-active PDF. |  | 1 Child Labour in Emergencies Toolkit. | Plan International, Alyson Eynon, independent consultant | TDH, IOM to collect feedback in Niger |  | March-August 2018
| 1.1.3 CL Toolkit: Translate final CL Toolkit in multiple languages (French, Arabic, Spanish) | Number of translated versions of the CLiE toolkit published as inter-active PDF. | 1 translation: Arabic | Cumulative of 3 translations (French, Spanish, Arabic) | Plan International, ILO |  |  |  | 2019-2020
| 1.1.4 CL Toolkit: Dissemination through webinars and email/webpages to local, national, regional and global platforms. | Number of webinars; number of knowledge sharing events conducted | 1 Webinar 3 local launch events (country level) | 2 webinars to launch the final toolkit (1 global and 1 for MENA region - see activity 1.5); 5 local launch events; 1000 downloads/copies. | Plan International, ILO |  |  | 2018-12-01 |  |  | 2500 | 1500 - consultancy fees; 1000 - printing of hardcopies | 2500 | Plan International | 3
| 1.1.5 CL Toolkit: A regional version of the CL Toolkit for MENA is developed based on extensive piloting in Middle East Region | Number of regional CL toolkits developed and published as inter-active PDF. |  | 1 regional MENA Child Labour in Emergencies Toolkit. | Plan International, ILO Regional Office of the Arab States (ROAS) | TDH |  | 2018-12-01 |  |  | 10000 | 10000 - Consultancy fees; 5000 - interactive PDF design | 5000 | Plan International | 10
| 1.2 Publish a report of lessons learned in CLiE based on learnings gathered during the 2017 toolkit field-testing phase | Number of reports published | 1 | 1 | Plan International, Alyson Eynon, independent consultant | ILO, CLTF members |  | 2018-12-01 |  |  | 5000 | 3000 - Consultancy fees; 2000 - Proof-reading, lay-out and printing | 3000 | Plan International | 6
| 1.3 Document good practices and lessons learned in child labour in emergencies programming. | Number of documented practices (case studies, videos, reports, etc.) | 10 | 25 |  |  |  | 2018-12-01 | 2019-2020 |  | 5000 | 5000 consultancy fees | 5000 | Plan International | 10
| 1.4 Collect new evidence (as well as good practices, lessons learned) widely available through global platfora, webinars, global events, etc. | Number of initiatives to share evidence and good practices (e.g. webinars, presentations during events, etc.) |  | 10 (webinar on New Global Estimates in first quarter of 2018; webinar on the new CLiE report published by CLTF in 2018) |  |  |  | 2018-12-01 | 2019-2020 |  | 2500 | 2500 consultancy fees | 2500 | Plan International | 5
| 1.5 Factsheet: Develop a Child Labour in Emergencies 2-page Factsheet for the Alliance incl. global definition, figures, resources and work of the CLTF. | Number of factsheets developed and published by the Alliance |  | 1 Factsheet |  | Plan International, ILO |  | 2018-10-01 |  |  | 0 | Consultancy fees for lay-out (graphic design) | 0
| 1.6 CPMS Revision: Revise the CPMS Child Labour Standard | The Child Labour Standard is revised and relevant inputs related to Child labour are provided to other CPMS. |  | 1 Child Labour standard | Plan, ILO and IOM | CLTF members |  | 2018-12-01 | 2019-2020 |  | 2500 | Consultancy fees | 2500 | Plan International | 5
| 1.6.1 CPMS Revision: Create and orientate Revision Group | Group members nominated and briefed |  | N/A | Plan, ILO and IOM |  |  | 2018-01-01
| 1.6.2 CPMS Revision: Conduct first round of revisions with practitioners at different levels | Pre-final draft circulated for feedback |  | N/A | Plan, ILO and IOM | CLTF members |  | Feb-March 2018
| 1.6.3 CPMS Revision: Provide inputs on child labour and trafficking to other revision groups |  |  | N/A | Plan, ILO and IOM |  |  | March-April 2018
| 1.6.4 CPMS Revision: Based on feedback finalise CPMS Child Labour Standard | Final version available |  | N/A | Plan, ILO and IOM |  |  | 2018-12-01 | 2019-2020
2. Capacity building: Humanitarian responders have enhanced knowledge and competencies to prevent and respond to (the worst forms of) child labour in emergencies | 2.1 F2F training module: Update the Child Labour module as part of the global Child Protection in Emergencies Face to Face (F2F) training, in collaboration with the LDWG under the Alliance. | Number of training modules updated |  | 1 Child Labour module | LDWG | CLTF members |  |  | 2019-2020 |  | 0 | Consultancy fees | 0 | Plan International
| 2.2. Online learning: Develop online learning resources on Child Labour in Emergencies (e.g. webinars, online learning modules) made available through global platfora, in collaboration with the LDWG under the Alliance. | Number of online learning resources developed | 1 online learning module, 1 webinar | 4 online learning resources (including 2 webinars, 2 online learning modules) |  | LDWG (update CL module), IOM (develop counter-trafficking in crisis online module) |  |  | 2019-2020 |  | 0 | Consultancy fees | 0
| 2.3 Case management module: Develop a child labour case management training module as part of the global CM Package in collaboration with the Case Management Task Force | Number of training modules developed |  | 1 Child Labour Case Management module | CMTF | CLTF members |  | 2018-12-01 |  |  | 7500 | Consultancy fees | 0
| 2.4 Technical Support: Unicef Turkey capacity building project | Numbe of agencies supported | 20 | 20 | Plan International | Unicef Turkey |  | 2018-07-01 |  |  | 36000 | Consultancy fees | 36000 | Unicef Turkey | 36
| 2.4.1 Provide remote technical support on CLiE to practitioners | Number of agencies/inter-agency initiatives supported |  | 20 |  |  |  |  | 2019-2020 |  | 10000 | Consultancy fees | 4000 | Plan International | 8
| 2.4.2 Provide in-country technical support to inter-agency child labour initiatives and implementation of the Child Labour in Emergencies Toolkit | Number of in-country support visits | 2 | 5 | Various | Various |  |  | 2019-2020
| 2.6 Develop M&E tools: Develop monitoring and evaluation tools to track impact of global CL toolkit and capacity building efforts on child labour, in collaboration with LDWG | Number of tools developed |  | 1 | ILO, Plan International | LDWG |  |  | 2019-2020
| 2.7 Learning survey: Conduct survey on learning needs and learning patterns in relation to Child labour among practitioners, in collaboration with the LDWG. | Number of learning surveys | 1 | 1 | CLTF lead agencies | LDWG |  |  | 2019-2020
| 2.8 Document local and global evidence, good practices, and lessons learned in child labour in emergencies programming. | Number of documented practices (case studies, videos, reports, etc.) |  | 25 | CLTF lead agencies | TdH |  |  | 2019-2020
| 2.9 Make good practices, lessons learned and evidence widely available through global platfora, webinars, global events, etc. | Number of initiatives to share evidence and good practices (e.g. webinars, presentations during events, etc.) |  | 10 (webinar on New Global Estimates in first quarter of 2018; webinar on the new CLiE report published by CLTF in 2018) | CLTF lead agencies |  |  |  | 2019-2020
| 2.10 Learning survey: Conduct survey on learning needs and learning patterns in relation to Child labour among practitioners, in collaboration with the LDWG. | Number of learning surveys | 1 | 1 | CLTF lead agencies | LDWG |  |  | 2019-2020
3. Coordination, policy and advocacy: Child labour in humanitarian settings is integrated/reflected in the agenda's of relevant global, regional and local platforms, including but not limited to the 8.7 Alliance and other Task Forces under the Alliance for Child Protection in Humanitarian Action. | 3.1 Inter-sector CLiE paper: Develop a paper on CLiE with Education and CALP/FSL sectors on how to jointly tackle Child Labour in Emergencies | Number of papers developed |  | 1 |  | ILO, Plan International |  | 2018-12-01
| 3.2 TF Coordination: Ensure coordination on CL in emergencies between humanitarian actors and between global initiatives | Number of calls and meetings |  | 4 task force calls per year, one face to face meeting every year. | ILO, Plan International | CLTF members |  | Quarterly
| 3.3 Donor mapping: conduct a donor mapping for Child Labour in Emergencies funding and influencing opportunities | Number of mappings |  | 1 | World Vision | Advocacy TF |  | 2018-10-01
| 3.4 Research: Conduct and advocate for research on CLiE | [7 empty] | 2019-2020
| 3.4.1 Set Child Labour in Emergencies research and advocacy/influencing priorities, in collaboration with Alliance 8.7 | Number of CL priorities included in Alliance 8.7 research initiatives |  | 2 | TF leads (Plan International and ILO) |  |  | One prioritisation exercise by April 2018 and one in 2020 to inform the 2021-22 work plan. | 2019-2020
| 3.4.2 Research: Based on the outcome of the AME WG research prioritisation exercise, initiate one research conducted under the global CLTF, led by two or more members of the CLTF, in collaboration with the AME working group | Number of research initiatives |  | 1 |  |  |  |  | 2019-2020 |  | 20000 | Research including primary data collection
| 3.5 Influence global initiatives, policy and advocacy work to include children in humanitarian context perspectives | Number of awareness raising and advocacy initiatives to which the CLTF actively contributes | 2 | 6 (2 per year - incl. 8.7 Alliance, global Alliance meetings, Child Labour conferences, international Day against Child Labour, etc.) |  |  |  | 2018 | 2019-2020
[6 empty] | Total: |  |  |  |  | 131000 |  | 90500
Note on H3: Administrator: We added this to make is easier for other WGs and TFs to track where their input may be needed. Pls fill.
Note on K3: Administrator: you could delete/hide this in this version. We will add it at the end of the year when we start reporting.
Note on G4: Comment from CLTF: Please sign up if your agency can contribute by reviewing one or more sections/tools of the toolkit
Note on G6: Comment from CLTF: Please sign up if your agency can contribute by reviewing one or more sections/tools of the toolkit
Note on B20: CLTF: This activity is not yet specified. Keep like this or better to identify a couple of specific sub activities? Altenatively we could specify the number of events and products.