## Draft CLTF WP 2020
GOAL: Humanitarian responders and development actors have the knowledge, skills and tools to implement quality and coordinated child labour in emergencies preparedness, prevention and response actions
WORK PLAN 2020-2021
OBJECTIVE | ACTIVITIES / Sub-Activities | INDICATOR | TARGET | LEAD | SUPPORTING WG/TF | CONTRIBUTING PARTNERS | Completed by | BUDGET REQUIRED 2020 | BUDGET REQUIRED 2021 | DESCRIPTION | BUDGET FUNDED | FUNDING GAP | FUNDING SOURCE
1. Technical tools, standards and guidance: Inter-agency Child Labour in Humanitarian Action Toolkit is available and disseminated at local, national, regional and global levels. | 1.1. Finalisation of revised Child Labour in Humanitarian Action Toolkits (global and MENA) | Number of global CL toolkits reviewed and finalised | 1 global toolkit, 1 MENA toolkit | Plan International (Alyson Eynon, consultant) | Cash TF, CMTF. External: CaLP, INEE, Education and FSL clusters | All CLTF members | Q1 2021 | 5000 | 0 | Design and editing of the toolkit | 5000 | 0 | Plan International
| 1.2 Translation CL Toolkit in multiple languages (French, Arabic, Spanish) | Number of translated versions of the CLiE toolkit published as inter-active PDF. | 3 (Arabic, French, Spanish) | CLTF Co-leads |  | Plan International, ILO, Right to Play | Q2 2021 |  | 65000 | Translation of the toolkit (toolkit, case studies and tools) into Arabic, French and Spanish | 35000 | 30000 | Plan International, ILO
| 1.3 Dissemination: CLTF microsite, newsletters, webinars, websites at local, national, regional and global level. | Number of webinars; clicks; number of knowledge sharing events conducted | 4 (2 online, 2 in-country) | Plan International, ILO, KM focal point Alliance Sectretariat | CaLP, FSL (external), All WGs/TFs | IOM, CP AoR, War Child UK | Q3+4 of 2021 | 0 | 0 | Done by CLTF coordinators / supported by project lead (pending funding) | 0 | 0
| 1.4 Launch for the global Child Labour in Humanitarian Actiontoolkit, for CP coordinators and practitioners. | Number of training events held | 1 global ToT + 2 regional ToTs | CLTF lead agencies | L&D WG, Advocacy WG | Plan, ILO ? | Q3+4 of 2020 | 0 | 0 | Online global launch with key speakers and country participants | 0 | 0
| 1.5 Develop an application to make the toolkit guidance and tools accessible to frontline workers | Application developed | 1 application | Plan International, ILO, KM focal point Alliance Sectretariat | L&D WG |  | Q3 2021 | 0 | 60000 | Developer costs, consultant, editing | 0 | 60000
| 1.6 Collect/Publish case studies on good practices and lessons learned in child labour in humanitarian action through Alliance (including COVID-19) | Number of documented practices (case studies, videos, reports, etc.) | 30 | Plan International, ILO, KM focal point Alliance Sectretariat |  | War Child UK | Q4 2020 and ongoing | 0 | 0 | By CLTF and project lead (3.1 pending funding) | 0 | 0
| 1.7 Develop a brief on the prevention of child labour in humanitarian action in line with the IA toolkit | Brief developed and disseminated | 1 brief | CLTF, Alliance Sectretariat |  |  | Q4 2021 | 0 | 0 | By CLTF and project lead (3.1 pending funding) | 0 | 0
2. Capacity building: Humanitarian responders have enhanced knowledge and competencies to prevent and respond to (the worst forms of) child labour in emergencies | 2.1 F2F training module: Update the Child Labour module as part of the global Child Protection in Humanitarian Action (F2F) training, in collaboration with the LDWG under the Alliance and development of CPMS e-course Child Labour | Number of training modules updated/e-course developed | 1 training module updated, 1 Child Labour CPMS e-course developed | CLTF, CPMS, L&D WG | L&D WG, CPMS | CLTF members | TBC | 0 | 15000 | By project lead (3.1 pending funding) | 15000 | 0 | CPMS (Save the Children Sweden)
| 2.2 Child Labour in Humanitarian Action training package. Develop training package on Child Labour in Humanitarian Action to support roll out of the toolkit (e.g. webinars, online learning modules) made available through CLTF microsite in collaboration with the LDWG under the Alliance. | Number of online learning resources developed | 2/3 online modules and 10/13 to be facilitated sessions |  | L&D WG | CLTF members | Q2 2021 | 0 | 20000 | Consultancy fees / technical fees - translation in French, Arabic and Spanish | 10000 | 10000 | L&D WG
| 2.3 Support and contribute to the online learning community on Child Protection in Humanitarian Action with Child Labour related content i.e. good practices, challenges etc3 | Number of members participating. | 1 learning community supported | CLTF |  | CLTF members; Alliance KM focal point, War Child UK, IOM | Q3+4 of 2021 | 0 | 0 | By project lead (3.1 pending funding) | 0 | 0
| 2.4 Provide remote technical support on Child Labour in Humanitarian Action to practitioners | Number of countries receiving support | 5 countries | CLTF |  | CP AoR (through help desks and RRT members) | Q1-Q4 2021 | 0 | 0 | By project lead (3.1 pending funding) | 0 | 0
| 2.5 Provide in-country technical support to inter-agency child labour initiatives on the roll-out and implementation of the Child Labour in Humanitarian Action Toolkit | Number of (rapid response) experts available to provide in-country technical support on behalf of the CLTF (NEW) | 2 experts available (consultants/rapid response team members) | CLTF |  | CP AoR (identification of in-country resources/experts, provide support through coordination/RRT) | Q3+4 of 2021 | 0 | 190000 | In-country implementation and technical support on-site | 0 | 190000
3. Coordination, policy and advocacy: Child labour in humanitarian settings is integrated/reflected in the agenda's of relevant global, regional and local platforms, including but not limited to the 8.7 Alliance and other Task Forces under the Alliance for Child Protection in Humanitarian Action | 3.1 TF Coordination: Ensure coordination on CL in Humanitarian Action between humanitarian actors and between global initiatives | Number of calls and meetings | 4 calls, 1 F2F/remote annual meeting | CLTF lead agencies |  | CLTF members | Ongoing | 0 | 80000 | Full time task force lead (project lead position) | 0 | 80000
| 3.2 CLTF Factsheet: Develop a Child Labour in Emergencies 2-page Factsheet for the Alliance incl. global definition, figures, resources and work of the CLTF. | Number of factsheets developed and published by the Alliance | 1 factsheet | CLTF lead agencies |  | Alliance secretariat, War Child UK, IOM | Q2 2021 | 0 | 0 | Layout and content of CL factsheet | 0 | 0
| 3.3 Inter-sector Child Labour in Humanitarian Action paper: Develop a paper on with Education and CALP/FSL sectors on how to jointly tackle Child Labour in Humanitarian Action | Number of papers developed | 1 paper | CLTF lead agencies | Potential collaboration with INEE? | Alliance Secretariat | Q1+Q2 of 2021 | 0 | 10000 | By project lead (3.1 pending funding) | 0 | 10000
| 3.4 Donor mapping: conduct and launch Child Labour donor mapping of funding and influencing opportunities | Number of report launched | 1 donor mapping report launched | World Vision International | Advocacy WG | Alliance KM focal point | TBC | 0 | 0 | By project lead (3.1 pending funding) | 0 | 0
| 3.5 Research Identify Child Labour in Humanitarian Action research and advocacy priorities, in collaboration with Alliance 8.7 | Number of actors participating in Child Labour research agenda | 1 research agenda developed | CLTF lead agencies | AME WG, | Alliance coordinators, CP AoR (assist in identification of topics and linking with country coordination groups), War Child UK, Columbia University. Potential support of intern. | 2021 | TBC | TBC |  | 0 | 0
| 3.6 KM Share learnings on "effective programme approaches to end WFCL" | Number of documented research practices | 1 documented practice | CPC Learning Network, WCUK | AME WG | Alliance coordinators | 2021 (ongoing) | 0 | 0 | By project lead (3.1 pending funding) | 0 | 0
| 3.7 Influence global initiatives, policy and advocacy work to include children in humanitarian context perspectives (2021 Year of Elimination of Child Labour) | Number of awareness raising and advocacy initiatives to which the CLTF actively contributes | 1 CL toolkit launch event for 8.7 Alliance held | CLTF lead agencies | Ext: Global CaLP, INEE, Education and FSL clusters. | Alliance coordinators, WCUK | 2020 (Q2-4) | 0 | 50000 | NY C - side-event in June 2021 on event "UN Year to Eliminate Child Labour" | 0 | 50000
[6 empty] | Total budget: |  | 5000 | 490000 |  | 65000 | 430000